## Sheet1
Botball Reigonal Goals
Team Members | Team Leader | Adult Sponser | Team Meeting Days
Ian Poorman | Ian Poorman | Mr. Culp | Monday
Ryan Landrum | Ryan Landrum |  | Wednesday
Teddy Schuerman | Teddy Schuerman
Connie Shen
Bianca Hill
Allison Birdsong
John Quinn Daily
Sunena Dahlvani
Jeremy Dowell
Kenton Scott
Goals
Week 1 | Due Date | Person Responsibilities | Status | Comments
create game board | 2007-02-09 | Mr.Culp and parents | completed | lots of hard work involved in putting together board such as scrubbing off glue
create botball project plan | 2007-02-09 | Sunena and Quinn | completed | had a hard time working together
choose team leadership | 2007-02-09 | all | completed | Ian, Teddy, and Ryan were our elected leaders by a unanimous vote
begin strategizing | 2007-02-09 | all | incomplete will do next week
create contract | 2007-02-09 | all | completed
create team organization | 2007-02-09 | all | completed
learn rules | 2007-02-09 | all | completed
assign jobs | 2007-02-09 | all | completed
write and update documentation site | 2007-02-09 | Sunena and Quinn | completed | had a hard time working together
get down a discipline sysytem | 2007-02-09 | Ian/ All | incomplete will do next week
week 2
finalize botball strategy | 2007-02-16 | all
start and get code library 50% complete | 2007-02-16 | Quinn/Sunena/Jeremy
write and upload documentation | 2007-02-16 | all
week 3
begin building robot #1 | 2007-02-23 | Kenton/Bianca
begin building robot #2 | 2007-02-23 | Kenton/Bianca
write and upload documentation | 2007-02-23 | all
have codeline library done | 2007-02-23 | Quinn/Sunena/Jeremy
week 4
have robot #2 chassis 50% done | 2007-03-02 | Kenton/Bianca
have robot #1 chassis 50% done | 2007-03-02 | Kenton/Bianca
begin programming robots | 2007-02-24 | Quinn/Sunena/Jeremy
write and upload documentation | 2007-03-02 | all
week 5
robot #1 chassis complete/ programming finished | 2007-03-09 | all
robot #2 chassis complete/ programming finished | 2007-03-09 | all
integration -check to see if they fit in the start box together | 2007-03-09 | all
integration- see if their projected paths are on top of each other | 2007-03-09 | all
integration- check measurements to regulations | 2007-03-09 | all
week 6
test robots | 2007-03-16 | all
refine robots and programs as neccesary | 2007-03-16 | all
write and upload documentaition | 2007-03-16 | all
week 7
test robots | 2007-03-23 | all
refine robots and programs as neccesary | 2007-03-23 | all
write and upload documentaition | 2007-03-23 | all
week 8
go to competiton | 2007-03-24 | all