## Sheet1
Botball Project Plan
Team Members: | Team Leader(s): | Team Meetings:
Stewart | Lei | Mon., Wed., Fri.
Andy | (vice)Rovy
Arlene | (treasurer)Ashley
Grace
Rogemson
Sharon
Ana
Bryan
Keao
craig
Ashley
Leischene(lei)
Kaiapuni
Rovy
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1:
Build Game Board
Buy PVC and board | Mr. Kido | Wed | complete
Cut PVC | kaiapuni | Mon
Assemble PVC | Rogemson,Andy,Rovy,Bryan,Craig,Arlene | Wed
Assemble 'volcano' | Rogemson | Wed
Learn Game Rules
Go over game slides | ALL | Fri
read and copy all manuels for team | ALL | M | complete | This happened during 1st meeting
Concept Ideas | All | M | complete | Bart had lots of ideas
Record concept ideas |  | M | complete
Botball Doc. site - assignment |  | M | complete | Lisa will update doc. site
Project Plan |  | F | complete | Maggie will update project plan and keep us on track
Week 2:
Concept ideas | ALL | M | complete | rejected ideas
Record rejected ideas |  |  | complete
Finish Game Board |  |  | complete
Recheck all measurements |  | M | Complete
Build mousetrap disperser |  | M | complete
Update project plan |  | M/W/F | complete
Inventory equipment |  | M/W | complete
purchase baggies and containers |  | M | complete
lable everything |  | W | complete
Begin models |  | W/F | in progress
Go through SolidWorks tutorial |  | W | complete
Doc. Site update |  | F | complete
Week 3:
Bot 1 - construction | Homer - all | M/W/F | in progress | Having trouble with PVC
Finalize construction plan | all | M | complete
gather materials | Homer | M | complete
Bot 2- construction | Marge/Lisa | M/W/F | in progress
Finalize construction plan | All | M | complete
Gather materials | Marge/Lisa | M | complete
Software - Bot 1 | Bart | W/F | in progress
Review IC | Bart | W | complete
Software - Bot 2 | Maggie | W/F | in progress | Camera having issues with blue
Review IC | Maggie | W | complete
Update project plan | Maggie | M/W/F | complete
Doc. Site update | Lisa | F | complete
Week 4:
Bot 1 - construction | Homer/Bart | M | COMPLETE!!!! | PVC is conquered!
Mobility | Homer/Bart | M | complete
Bot 2 - construction | Marge/Lisa | M/W/F | COMPLETE!!!!
Mobility | Marge/Lisa | M | complete
Integration - Bot 1 | Homer/Bart | W/F | in progress
Mobility | Homer | W/F | complete
Integration with Bot 2 | bart | W/F | in progress
Integration - Bot 2 | Marge/Maggie/Lisa | W/F | in progress
Mobility | Marge/Lisa | W | complete
Integration with Bot 1 | Maggie |  | in progress
Update project plan | Maggie | M/F | complete
Doc. Site update | Lisa | F | complete
Week 5:
Integration - Bot 1 | Homer/Bart | M/W/F | in progress
Testing - seeding and DE | ALL | M/W/F | Complete
Software tweaks - Bot 1 | Bart | W/F | in progress | Tweaked seeding round and DE
Integration - Bot 2 | Marge/Lisa | M/W/F | in progress
Testing - seeding and DE | ALL | M/W/F | Complete
Software tweaks - Bot 2 | Lisa | W/F | Complete | Tweaked seeding code
Update project plan | Maggie | W/F | complete
Doc. Site update | Lisa | W/F | complete
On-Site Presentation | Maggie/Lisa | M/W/F | in progress | Use info. From project plan and doc. site; make poster and book
Week 6:
Update project plan | Maggie | M/W | complete
Doc. Site update | Lisa | M/W | complete
Integration | Bart/Lisa | M/W/F | complete
Seeding tweaks - Bot 1 | Bart | W | complete
DE tweaks - Bot 1 | Lisa | M/W | complete
Integration | Bart/Lisa | M/W/F | complete
Seeding tweaks - Bot 2 | Bart | F | complete
DE tweaks - Bot 2 | Lisa | M | complete
On-Site Presentation | Maggie/Lisa | F | complete | Practiced in front of Mr. Burn's class
Note on A17: Milestones will be written in bold italics and tasks will have a regular font