## Sheet1
Botball Project Plan
Team Members: | Team Leader(s): | Team Meetings:
Stewart | Lei | Mon., Wed., Fri.
Andy | (vice)Rovy
Arlene | (treasurer)Ashley & Arlene
Grace
Rogemson
Sharon
Ana
Bryan
Keao
craig
Ashley
Leischene(lei)
Kaiapuni
Rovy
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1:
Build Game Board
Buy PVC and board | Mr. Kido | Wed | complete
Cut PVC | kaiapuni | Mon
Assemble PVC | rogemson,arlene,craig,andy,bryan | Wed
Assemble 'volcano' | Rogemson | Wed
Learn Game Rules |  | Wed |  | We started it during the 1st meeting
Go over game slides | Team Leader(s): | Fri
read and copy all manuels for team | Ms.Nathansen | M | complete | This happened during 1st meeting
Concept Ideas | the team | M | complete
Record concept ideas | rovy,ana,grace,ashley | M | complete | we decided it to have 2 bots, one with an arm to grab the balls with and one with scooper to scoop up stuffs that fell.
Botball Doc. site - assignment | lei | M | complete
Project Plan | the whole team | F | complete | Leischene will update project plan and keep us on track
Week 2:
Concept ideas |  |  |  | we rejected the ideas of having just one bot to do everything scoop and grab, so that’s why we have to bots.
Record rejected ideas |  |  | incomplete
Finish Game Board
Recheck all measurements | kaiapuni |  | complete
Build mousetrap disperser | craig, kaiapuni |  | complete
Update project plan | lei |  | complete
Inventory equipment |  |  | complete | purchase tool box for lego parts
purchase baggies and containers
label everything
Begin models | keao, kaiapuni, andy,craig |  | in progress
Go through SolidWorks tutorial | kaiapuni |  | during workshop
Doc. Site update | lei |  |  | we started the documentation but we werent sure how to upload the file so we missed the deadline
Week 3:
Bot 1 - construction
Finalize construction plan | keao, kaiapuni, and andy | Wednesday, march 14, 2007 & Friday, march 16, 2007 | in progress | Andy and Keao is working on a bot with a claw, that allows the bot to pick up the blue balls (ocean/water)and also to move the houses into the base.
gather materials
Bot 2- construction
Finalize construction plan | keao,kaiapuni,craig and andy | Wednesday, march 14, 2007 & Friday, march 16, 2007 |  | Kaiapuni is working on a bot that has a scooper to scoop up all the small balls (pineapples).
Gather materials | keao and kaiapuni
Software - Bot 1
Review IC | rogemson | wed | in progress | review online course
Software - Bot 2
Review IC
Update project plan | ana,rovy,arlene.ashley | Wed 3/14/ 2007 & Friday, 3/16/2007
Doc. Site update
Week 4:
Bot 1 - construction | kaiapuni | wed 3/21/07 &Friday,3/23/07 | in progress | kaiapuni is working on a new scooper it was too long so he's making it shorter so it can reach the bins
Mobility
Bot 2 - construction | keao | wed 3/21/07 &Friday,3/23/07 | in progress | keao is building a base but still not done.
Mobility
Integration - Bot 1
Mobility | kaiapuni | wed 3/21/07 &Friday,3/23/07 | in progress
Integration with Bot 2
Integration - Bot 2
Mobility
Integration with Bot 1 | kaiapuni | wed 3/21/07 &Friday,3/23/07 | in progress
Update project plan | grace,arlene,ana
Doc. Site update
Week 5:
Integration - Bot 1
Testing - seeding and DE
Software tweaks - Bot 1 |  |  |  | Tweaked seeding round and DE
Integration - Bot 2
Testing - seeding and DE
Software tweaks - Bot 2 |  |  |  | Tweaked seeding code
Update project plan
Doc. Site update
On-Site Presentation |  |  |  | Use info. From project plan and doc. site; make poster and book
Week 6:
Update project plan
Doc. Site update
Integration
Seeding tweaks - Bot 1
DE tweaks - Bot 1
Integration
Seeding tweaks - Bot 2
DE tweaks - Bot 2
On-Site Presentation |  |  |  | Practiced in front of Mr. Burn's class
Note on A17: Milestones will be written in bold italics and tasks will have a regular font