## 2007 Schedule
Team Members
Liz,Taylor,Justin,Ellie,Eli,Cheyenne,Mrs. Fortner
| Task | Responsible Team Member(s) | Start Date | Completion Date | Status | Notes
Week 1 | Review of Tournament Rules | All | 2007-01-16 |  | on-going
01/16/07-01/19/07 | Purchases Game Board Parts | Mrs. Fortner | 2007-01-19 |  | on-going
| Begin Game Board Construction | Mr. & Mrs. Fortner | 2007-01-19 |  | on-going
| Copy and Read Manual for team | All | 2007-01-16 |  | on-going
| Research Botball website | All | 2007-01-16 |  | on-going
| Explore Teams Only Botball Website | All | 2007-01-16
| Develop Project Plan | Taylor, Wyatt, and Liz | 2007-01-18 |  | on-going
| Present Information from Workshop | Mrs. Fortner, Eli, Ellie | 2007-01-16
Week 2 | Purchase More Game Board Pieces | Mrs. Fortner | 2007-01-21 | 2007-01-22 | Complete
01/22/07-01/26/07 | Construct Game Board | Mr. Fortner | 2007-01-21 | 2007-01-24 | Complete
| Visited FAQ on website | Wyatt & Liz | 2007-01-25 |  | On-Going
| T-Shirt Design | All | 2007-01-24 | 2007-01-24 | Complete
| Robot Designs & Names | All | 2007-01-22 |  | On-Going
| Review rules & scoring | Ellie, Liz, Cheyenne, Taylor | 2007-01-24 |  | On-Going
| Begin building 2nd robot | Ellie, Liz, Cheyenne, Taylor | 2007-01-24 |  | On-Going
| Met with mentor, Miss LaJean | All | 2007-01-26 |  |  | She helped with sensor and motor information
Week 3 | Discussed robot designs and possible | All |  |  | 0n-Going
01/29/07-02/02/07 | points that could be scored | All | 2007-01-29 | 2007-01-29 | completed
| Tested (ouch!) mouse trap | All | 2007-01-29 |  | on-going
| Robot base built | All | 2007-01-29
| Wyatt drops out | Wyatt | 2007-01-31 | 2007-01-31 | completed
| Uploaded botball prodject plan | Liz,Justin,Taylor | 2007-01-31 |  | on-going
| typed out rejected design concepts | Ellie,Liz,Taylor | 2007-01-31 | 2007-01-31 | completed
| Decided to go with one robot | All | 2007-01-31 | 2007-01-31 | completed | Too hard to do two robots!!!!!!!!!!!!!!!!!!!
| got wheels on robot | Taylor,Justin,Liz,Ellie | 2007-02-01 | 2007-02-01 | completed
| looked over robot | Justin,Liz,Taylor,Ellie | 2007-02-01 |  | on-going
Week 4 | Robot moves!!! We celebrate!!! | All | 2007-02-06 |  | on-going | Very Happy!!!!!!!!!!!!!!!!
02/05/07-02/09/07 | Having difficulties with firmware | All | 2007-02-06 | 2007-02-06 | completed
| Decided to have extra robot | All | 2007-02-08 | 2007-02-08 | on-going | we are going to try to have a back-up robot
| Went over extra documentation | Taylor,Liz | 2007-02-08 |  | on-going
| made robot move in wrong direction | Ellie | 2007-02-06 |  | on-going | we are trying to get our robots going correctly
| working on table layouts | Liz,Taylor | 2/8-2/9/07 |  | on-going
| sketches and notes for table layout | Liz,Taylor | 2007-02-08 |  | on-going | still trying to complete that
| programing both robots | All | 2007-02-05 |  | on-going
Week 5 | Had to rebuild second robot (Bonnie) | Ellie,Justin | 2007-02-12 |  | on-going
2/12/07-2/16/07 | Studing flow charts | Liz,Taylor | 2007-02-13 |  | on-going
| Programming first robot (Clyde) | Ellie,Justin,Eli | 2007-02-13 |  | on-going
| Downloaded Edrawlings | Liz,Taylor | 2007-02-13 | 2007-02-13 | completed
| Mrs. Fortner had workshops and we met at 2 times last week |  | 2007-02-14
| We also met with 4-Hers and went over information needed |  | All | 2007-02-14
Week 6 | Named Bonnie and Clyde | All | 2007-02-20 | 2007-02-20 | completed | We all thought of names and decided on Bonnie and Clyde
02/19/07-02/23/07 | We met with the 4-Hers again | All | 2007-02-20
Week 7
??/??/07 - ??/??/07
`