## Sheet1
Botball Project Plan
Team Members: | Team Leader: | Team Meetings:
Carolyn | Jeff | Wed., Fri.
Daniel |  | 3:00 - 5:00 PM
James
Jeff
Mathew
Mike
Nathan
Ryan
William
Milestones/Tasks | Assignment | Status | Notes
Week 1: Wednesday
Assemble Game Board
Review Materials | ALL | complete
Cut PVC To Length | ALL | complete
Assemble Parts | ALL | complete | Missing Some Parts For Volcano
Note Missing Parts | ALL | complete
Review Game Rules
Review Game rules | Jeff (Leader)/All | complete
Hardware
Review Hardware | ALL | complete
XBC V3 | ALL | complete
Lego Parts | ALL | complete
Electronic Parts | ALL | complete
Week 1: Friday
Concept ideas
Continue Discussion | ALL | complete
Select Best Ideas | ALL | complete
Split Into Teams | ALL | complete
Finish Game Board
Build Volcano | ALL | complete | Still Short 45 Degree Elbows
Test Mousetrap | ALL | complete
Hardware Team
Start Prototyping Effectors | HARDWARE | complete
Prototype Arm | HARDWARE | complete
Software Team
Configure Camera And Experiment | SOFTWARE | complete
Test Light Sensors For Color Detection | SOFTWARE | complete
Week 2: Wednesday
Hardware Team
Started Building Both Bots | HARDWARE
Software Team
Contiued Camera Tests | SOFTWARE
Formulated Plans For Programming | SOFTWARE
Building The Table
Completed Volcano | ALL | complete
Tested Volcano | ALL | complete
Week 2: Friday
Hardware Team
Continued Building Both Bots | HARDWARE |  | plan to be done soon
Software Team
Finished Camera Tests | SOFTWARE
Continued Formulating Software Plan | SOFTWARE |  | hope to start the actual programming soon
Week 3: Wednesday
Hardware Team
Continued Building | HARDWARE |  | bot 01 has moved successfully!
Week 3: Friday
Week 4: Wednesday
Week 4: Friday
Week 5: Wednesday
Week 5: Friday
Week 6: Wednesday
Note on A12: Milestones will be written in bold italics and tasks will have a regular font