## Sheet1
Botball Project Plan
Team Members: | Team Leader: | Team Meetings:
Chris Hume | Group Consensus | Tuesday
Matt Pittman |  | Wednesday
Adam Fitts
John Dachoute
Hasseb Qazizada
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1:
Build Game Board
Buy PVC and board | Group | Tuesday 2/06/07 | Done
Cut PVC | Group | Tuesday 2/06/07 | Done
Assemble PVC | Group | Tuesday 2/06/07 | Done | Finished half- board
Assemble 'volcano' | Group | Tuesday 2/06/07 | Done
Learn Game Rules
Go over game slides | Group | Tuesday 1/30/07 | Done | whole team there
read and copy all manuals for team | Group | Tuesday 1/30/07 | Done | We kept it computer based
Concept Ideas
Record concept ideas | Matt, Chris | Tuesday 1/30/07 | Done | Have it on paper
Botball Doc. site - assignment | Adam | Tuesday 1/30/07 | Done | Started
Project Plan | All | Tuesday 1/30/07 | Done | Have updated it
Concept ideas
Record rejected ideas | Adam | Tuesday 1/30/07 | Done | Have it on paper
Finish Game Board
Recheck all measurements | Group | Tuesday 2/06/07 | Done | Cut pieces and put together
Build mousetrap disperser | Group | Tuesday 2/06/07 | Done | built and tested
Update project plan | Group | Tuesday 2/06/07 | Done | updated
Inventory equipment
purchase baggies and containers | Group | Tuesday 2/06/07 | Done | Teacher did
label everything | Group | Tuesday 2/06/07 | Done | labeled all items
Begin models
Go through SolidWorks tutorial | Group | Tuesday 2/06/07 | Done | Decided one team member would do this, it was Matt
Doc. Site update | Adam | Tuesday 1/30/07 | Done | happening daily
Week 2:
Bot 1 - construction
Finalize construction plan | Matt | Tuesday 02/06/07 | Done | have design done
gather materials | Matt | Tuesday 02/06/07 | Have started | all parts sorted and easily accessible
Bot 2- construction
Finalize construction plan | Chris | Tuesday 02/06/07 | Done | have design done
Gather materials | Chris | Tuesday 02/06/07 | Have started | all parts sorted and easily accessible
Software - Bot 1 | Matt |  |  | Will do once construction complete
Review IC | Matt |  |  | looking over the ic program
Software - Bot 2 | Matt |  |  | Will do once construction complete
Review IC | Matt |  |  | looking over the ic program
Update project plan | Group | Tuesday 02/06/07 | Updated
Doc. Site update | Adam | Tuesday 02/13/07 | Done
Week 3:
Bot 1 - construction
Mobility | Matt |  | have started
Bot 2 - construction
Mobility | Chris |  | have started
Integration - Bot 1
Mobility | Matt, Chris
Integration with Bot 2 | Matt, Chris
Integration - Bot 2
Mobility | Matt, Chris
Integration with Bot 1 | Matt, Chris
Update project plan | Group
Doc. Site update | Adam
Week 4:
Integration - Bot 1
Testing - seeding and DE | Group
Software tweaks - Bot 1 | Matt
Integration - Bot 2
Testing - seeding and DE | Group
Software tweaks - Bot 2 | Matt
Update project plan | Group
Doc. Site update | Adam
On-Site Presentation | Adam
Week 5:
Update project plan | Group
Doc. Site update | Adam
Integration
Seeding tweaks - Bot 1 | Group
DE tweaks - Bot 1 | Group
Integration
Seeding tweaks - Bot 2 | Group
DE tweaks - Bot 2 | Group
On-Site Presentation | Group
Note on A9: Milestones will be written in bold italics and tasks will have a regular font