## Sheet1
Botball Project Plan
Team Members: | Team Leader: | Team Meetings: | Coach
Angus Schaefer (mech) | Joel Overly/Bryan Humlie | Tues After school | Ms. A
Kelly Waliser(mech) |  | M-W-F Tutorial
Chris Miller(mech)
Cody Suttles(mech)
George Lamphere(mech)
Cameron McMillan(mech)
Austin Cluff (programmer)
Ben Harris (programmer)
Bryan Humlie (programmer)
Will Horne (programmer)
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1 (2/19):
Build Game Board
Buy PVC and board | Ms. A | W/F | done
Cut PVC | Ms. A | F
Assemble PVC | Team | F
Assemble 'volcano' | Team | F
Learn Game Rules
Go over game slides | Team
Concept Ideas | Team | M | complete | Emphasis on capping the volcano
Record concept ideas | Team | M | complete
Botball Doc. site - assignment | Team | M |  | Ben & Bryan
Project Plan | Team |  | complete | Group task so far
Week 2 (2/26):
Concept ideas | ALL | M | incomplete | completed 3/5
Record rejected ideas |  | M | incomplete | completed 3/5
Finish Game Board | Team | M | complete
Recheck all measurements | Team | M | Complete
Update project plan | Austin | M/W/F | complete
Inventory equipment | Kelly | M/W | complete
Begin models | Team | W/F | in progress
Build chassis | Cody | m/w/f | in progress
Test claws and scoops | Team | m/w/f | in progress
Doc. Site update | Austin | F | complete
Week 3 (3/5):
Finish Game Board | Team |  | complete | secure PVC to board
Assemble 'volcano' | Team |  | complete
Bot 1 - construction | Team | M/W/F | in progress
Finalize construction plan | Team | M | in progress
gather materials | Ms. A | M | complete | rubber bands & paper
Bot 2- construction | team | M/W/F | in progress
Finalize construction plan | Team | M | in progress
Gather materials | Ms. A | M | complete
Software - Bot 1 | Will/Bryan | W/F | in progress
Review IC | Will/Bryan | W | complete
Software - Bot 2 | Ben/Austin | W/F | in progress
Review IC | Ben/Austin | W | in progress
Update project plan | Austin | M/W/F | complete
Doc. Site update | Bryan | F |  | technical difficulties!
Week 4 (3/12):
Bot 1 - construction | mechs | M
Mobility |  | M
Bot 2 - construction | mechs | M/W/F
Mobility | mechs | M
Integration - Bot 1 | programmers | W/F
Mobility | mechs | W/F
Integration with Bot 2 | programmers | W/F
Integration - Bot 2 | programmers | W/F
Mobility | mechs | W
Integration with Bot 1 | programmers
Update project plan | Austin | M/F
Doc. Site update | Bryan | F
Week 5 (3/19):
Bot 1 - construction
Bot 2 - construction
Week 6 (3/26):
Bot 1 - construction
Bot 2 - construction
Week 7 (4/2) Spring Break:
Week 8 (4/9):
Integration - Bot 1 |  | M/W/F
Testing - seeding and DE | ALL | M/W/F
Software tweaks - Bot 1 |  | W/F |  | Tweaked seeding round and DE
Integration - Bot 2 |  | M/W/F
Testing - seeding and DE |  | M/W/F
Software tweaks - Bot 2 |  | W/F |  | Tweaked seeding code
Update project plan |  | W/F
Doc. Site update |  | W/F
On-Site Presentation |  | M/W/F |  | Use info. From project plan and doc. site; make poster and book
Week 9 (4/16):
Update project plan |  | M/W
Doc. Site update |  | M/W
Integration |  | M/W/F
Seeding tweaks - Bot 1 |  | W
DE tweaks - Bot 1 |  | M/W
Integration |  | M/W/F
Seeding tweaks - Bot 2 |  | F
DE tweaks - Bot 2 |  | M
On-Site Presentation | Cameron | F |  | Practiced in front of Mr. Burn's class
Note on A14: Milestones will be written in bold italics and tasks will have a regular font