## Sheet1
PROJECT PLAN AS OF MARCH 7, 2007
TEAM MEMBERS | TEAM MENTOR
Jeremy Aylard | Ms. Irene Teninty
Jonathan Aylard
Jeff Chan
Katherine Huynh
James Kuo
Rahul Nayak
Travis Ruffin
Jacqueline Tran
Justin Vachon
Thomas Yee |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
TASK/EVENT | PERSON(S) INVOLVED | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa
Botball Tutorial
Building the Demobot | Jeff Chen/James Kuo/Rahul Nayak/ | bar: Week 1 Su
Katherine Huynh/Jacqueline Tran | bar: Week 1 Su
Programming the Demobot | Jeff Chen/James Kuo/Rahul Nayak | bar: Week 1 Su
Building the Game Board
Cutting/Measuring the PVC Pipes | Jeremy Aylard/Jonathan Aylard/Jeff Chan/ | bar: Week 1 Su to Week 3 W
Katherine Huynh/James Kuo/Rahul Nayak/ | bar: Week 1 Su to Week 3 W
Travis Ruffin/Jacqueline Tran/Justin Vachon | bar: Week 1 Su to Week 3 W
Assembling the PVC Pipes | Jonathan Aylard | bar: Week 1 Tu to Week 3 F
Assembling the Game Board | Jonathan Aylard/Jeremy Aylard | bar: Week 1 Tu to Week 3 F
Justin Vachon/Travis Ruffin | bar: Week 1 Tu to Week 3 F
Assembling the Volcano | Jeremy Aylard/Jonathan Aylard/ | bar: Week 1 Th to Week 3 Sa
Justin Vachon/Travis Ruffin | bar: Week 1 Th to Week 3 Sa
Assembling Mousetrap Disperser | Jeremy Aylard/Jonathan Aylard/ | bar: Week 1 Th to Week 3 Sa
Justin Vachon/Travis Ruffin | bar: Week 1 Th to Week 3 Sa
Documentation
Project Plan | Rahul Nayak/Jacqueline Tran | bar: Week 1 Su to Week 3 W
Initial Design | Rahul Nayak/Jacqueline Tran | bar: Week 1 Su to Week 3 W
Rejected Design | Rahul Nayak/Jacqueline Tran | bar: Week 1 Su to Week 3 W
Programming the Robot
Creating Simple Functions | Jeff Chan/Rahul Nayak | bar: Week 1 Su to Week 4 Su
Testing New Functions | Jeff Chan/Rahul Nayak | bar: Week 1 Su to Week 3 W
Learning New Commands | Jeff Chan/Rahul Nayak | bar: Week 1 Su to Week 3 W
Designing the Robot
Using SolidWorks to Build a Model | Jacqueline Tran/Katherine Huynh/James Kuo | bar: Week 1 Tu to Week 3 W
Building the Robot
Sorting Lego Pieces | Katherine Huynh/James Kuo/Thomas Yee | bar: Week 1 M to Week 3 Su
Attaching Sensors | James Kuo | bar: Week 4 Su to Week 5 Tu
Shielding Light Sensors | James Kuo/Rahul Nayak | bar: Week 2 M to Week 2 F
Attaching Motors | James Kuo, Jacqueline Tran | bar: Week 5 M to Week 6 Su
Katherine Huynh/Thomas Yee
Readying Up Motors for Use | James Kuo/Rahul Nayak | bar: Week 1 Su to Week 1 W
Actual Building | Jeremy Aylard/Jonathan Aylard/James Kuo/ | bar: Week 2 Sa to Week 3 W; Week 5 F to Week 6 F
Katherine Huynh/Jacqueline Tran/Thomas Yee | bar: Week 2 Sa to Week 3 W; Week 5 F to Week 6 F
Team Communication
Google Groups | Jacqueline Tran | bar: Week 1 Su
Collection of Names and Emails | Katherine Huynh | bar: Week 1 Su
Finished Robot
Testing the Robot | James Kuo/Jeff Chan/Rahul Nayak | bar: Week 1 Su to Week 3 Th
Improvements | James Kuo/Jeff Chan/Rahul Nayak | bar: Week 1 Su to Week 4 Su
Fixing the Programs | Rahul Nayak/Jeff Chan | bar: Week 1 Su to Week 3 W; Week 3 Sa to Week 4 Sa
Seeding Runs | Rahul Nayak/Jeff Chan | bar: Week 1 Su to Week 3 W; Week 6 W to Week 7 W
Team vs Team Runs | Rahul Nayak/Jeff Chan | bar: Week 1 Su to Week 3 W; Week 6 F to Week 7 Th
LEGEND | COLOR
Not Yet Worked On
To Be Started
Just Started
In Progress
Delayed
Expected to be finished
Finished