## Sheet1
BOTBALL PROJECT PLAN
Team Members: |  | Team Leaders: | Team Meetings:
Alice Lu |  | Alex Kennedy | Fridays
Kate Kingsbury |  | Dr. Hundal
Talel
Sam Woloszynski | New Member
Botty Botterkins the Third
Milestones/Tasks |  | Assignment | Day | Status | Notes
Week 1:
Build Game Board |  | Whole Team | Done before Project Plan was created | Complete
Buy PVC and board |  | Alex Kennedy | Done before Project Plan was created | Complete
Cut PVC |  | Adults on Team | Done before Project Plan was created | Complete
Assemble PVC |  | Not Sure Yet… | Done before Project Plan was created | Complete
Assemble 'volcano' |  | Not Sure Yet… | Meeting On April 20th | Complete
Learn Game Rules |  | Whole Team | Meeting On April 13th | Complete
Go over game slides |  | Whole Team | Meeting On April 13th | Complete
Read and copy all manuals for team |  | Adults on Team | Done on Assigned Member's Time | Complete
Concept Ideas |  | Whole Team | Go over at Next Meeting | Complete
Record concept ideas |  | Alice Lu | Done on Assigned Member's Time | Complete
Botball Doc. Site - assignment |  | Alice and Kate | Done on Assigned Member's Time | Complete
Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | Complete
Week 2:
Concept Ideas |  | Whole Team | Go over at Next Meeting | Complete
Record rejected ideas |  | Alice Lu | Done on Assigned Member's Time | Complete
Finish Game Board |  | Adults on Team | Done on Assigned Member's Time | Complete
Recheck all measurements |  | Talel | Meeting On April 13th | Complete
Build mousetrap disperser |  | Not Sure Yet… | Done on Assigned Member's Time | Complete
Update project plan |  | Kate Kingsbury | Done on Assigned Member's Time | Complete
Inventory equipment |  | John | Meeting On April 20th | Complete
Purchase baggies and containers |  | Not Sure Yet… | Done on Assigned Member's Time | Complete
Label everything |  | Kate Kingsbury | Done on Assigned Member's Time | Complete
Begin Models |  | Whole Team | Meeting On April 20th | Complete
Go through SolidWorks tutorial |  | Whole Team | Meeting On April 13th | Complete
Doc. Site update |  | Alice and Kate | Meeting On April 13th | Complete
Week 3: |  |  |  | Complete
Bot 1- Construction |  | Whole Team | Meeting On April 20th | Complete
Finalize construction plan |  | Talel | Done on Assigned Member's Time | Complete
Gather materials |  | Whole Team | Go over at Next Meeting | Complete
Bot 2- Construction |  | Whole Team | Meeting On April 20th | Complete
Finalize construction plan |  | John | Done on Assigned Member's Time | Complete
Gather materials |  | Whole Team | Go over at Next Meeting | In Progress
Software- Bot 1 |  | Whole Team | Meeting On April 20th | In Progress
Review IC |  | Alice and Kate | Done on Assigned Member's Time | In Progress
Software- Bot 2 |  | Whole Team | Meeting On April 20th | In Progress
Review IC |  | Alice and Kate | Done on Assigned Member's Time | In Progress
Update Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | In Progress
Doc. Site update |  | Alice and Kate | Done on Assigned Member's Time | In Progress
Week 4: |  |  |  | In Progress
Bot 1- Construcion |  | Whole Team | Meeting On April 27th | Complete
Mobility |  | Talel | Done on Assigned Member's Time | Complete
Bot 2- Construcion |  | Whole Team | Meeting On April 27th | Complete
Mobility |  | John | Done on Assigned Member's Time | Complete
Integration- Bot 1 |  | Whole Team | Meeting On April 27th | In Progress
Mobility |  | Talel | Done on Assigned Member's Time | In Progress
Integration with Bot 2 |  | Alice and Kate | Done on Assigned Member's Time | In Progress
Integration- Bot 2 |  | Whole Team | Meeting On April 27th | In Progress
Mobility |  | John | Done on Assigned Member's Time | In Progress
Integration with Bot 1 |  | Alice and Kate | Meeting On April 27th | In Progress
Update Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | In Progress
Doc. Site update |  | Alice and Kate | Done on Assigned Member's Time | In Progress
Week 5: |  |  |  | Incomplete
Integration- Bot 1 |  | Whole Team | Meeting On May 4th | Incomplete
Testing- Seeding and DE |  | Talel and John | Done on Assigned Member's Time | Incomplete
Software tweaks- Bot 1 |  | Alice and Kate | Done on Assigned Member's Time | Incomplete
Integration- Bot 2 |  | Whole Team | Meeting On May 4th | Incomplete
Testing- Seeding and DE |  | Talel and John | Done on Assigned Member's Time | Incomplete
Software tweaks- Bot 2 |  | Alice and Kate | Done on Assigned Member's Time | Incomplete
Update Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | Incomplete
Doc. Site update |  | Alice and Kate | Done on Assigned Member's Time | Incomplete
On-Site Presentation |  | Not Sure Yet… | Go over at Next Meeting | Incomplete
Week 6: |  |  |  | Incomplete
Update Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | Incomplete
Doc. Site update |  | Alice and Kate | Go over at Next Meeting | Incomplete
Integration |  | Whole Team | Meeting On May 11th | Incomplete
Seeding tweaks- Bot 1 |  | Talel and John | Done on Assigned Member's Time | Incomplete
DE tweaks- Bot 1 |  | Alice and Kate | Done on Assigned Member's Time | Incomplete
Integration |  | Whole Team | Meeting On May 11th | Incomplete
Seeding tweaks- Bot 2 |  | Talel and John | Done on Assigned Member's Time | Incomplete
DE tweaks- Bot 2 |  | Alice and Kate | Done on Assigned Member's Time | Incomplete
On-Site Presentation |  | Not Sure Yet… | Go over at Next Meeting | Incomplete
Week 7:
Update Project Plan |  | Kate Kingsbury | Done on Assigned Member's Time | Incomplete
Doc. Site Peer Review |  | Alice and Kate | Go over at Next Meeting | Incomplete
Doc. Site Update and Final Plan |  | Alice and Kate | Go over at Next Meeting | Incomplete
Integration |  | Whole Team | Go over at Next Meeting | Incomplete
Trials |  | Whole Team | Go over at Next Meeting | Incomplete
Seeding Trial- Bot 1 |  | Whole Team | Go over at Next Meeting | Incomplete
Competition Simulation- Bot 1 |  | Whole Team | Go over at Next Meeting | Incomplete
Trials |  | Whole Team | Go over at Next Meeting | Incomplete
Seeding Trial- Bot 2 |  | Whole Team | Go over at Next Meeting | Incomplete
Competition Simulation- Bot 2 |  | Whole Team | Go over at Next Meeting | Incomplete
Week 8:
Finalize Doc. Site |  | Alice and Kate | Go over at Next Meeting | Incomplete
Practice Doc. Site |  | Alice and Kate | Go over at Next Meeting | Incomplete
Software Tweaks |  | Whole Team | Go over at Next Meeting | Incomplete
Final Tweaks on Bot 1 |  | Talel | Done on Assigned Member's Time | Incomplete
Final Tweaks on Bot 2 |  | Talel | Done on Assigned Member's Time | Incomplete
Software Go? |  | Whole Team | Go over at Next Meeting | Incomplete
Make Sure Bot 1 Software is Go |  | Sam Woloszynski | Go over at Next Meeting | Incomplete
Make Sure Bot 2 Software is Go |  | Sam Woloszynski | Go over at Next Meeting | Incomplete
Go over at Next Meeting
Done on Assigned Member's Time
Done before Project Plan was created
Meeting On May 11th
Meeting On May 4th
Meeting On April 27th
Meeting On April 20th
Meeting On April 13th
Talel
Alice and Kate
Not Sure Yet…
Adults on Team
Whole Team
Alice Lu
Kate Kingsbury
Talel
Sam Woloszynski
John
Alex Kennedy
Dr. Hundal
Incomplete
In Progress
Complete

## Sheet2
J
K
L